## Proprosal Timeline
2025-12-31 | Enter Date Due to Sponsor
2025-12-22 | Final proposal docs due in sponsor's portal and Kuali
PROPOSAL TASKS
PI | Analyst | Due | Date Completed | If Late
Submit Request for Budget Proposal |  | 2025-11-21 |  | PI launches their own Kuali
Provide Budget Needs |  | 2025-11-21 |  | Notification less than 7 days can result in the inability to provide a budget that aligns with institutional & sponsor policy
Read Sponsor Notice | Read Sponsor Notice |  |  | Analysts are unable to commit to reading the RFP if it's provided 2 days prior to SPA's due date.
| Launch Kuali proposal, add aggregators, upload RFA to "internal" tab, answer questionnaire, add key personnel effort. Share Kuali link w/PI | 2025-11-25 |  | PI launches their own Kuali
| Launch Proposal in sponsor's portal. Share proposal link with PI | 2025-11-25 |  | PI Launches their own proposal
Create online application folder in PI folder
| First Draft of Budget to PI | 2025-12-04
Provide CoPI and Administrative contacts | Analyst will create list for PI of what is due from CoPIs | 2025-12-04 |  | PI creates lists and emails CoPIs
| Create list of items required for proposal submission | 2025-12-15
| Final Budget | 2025-12-15
| Final CoPI documents on sponsor templates are due and reviewed | 2025-12-15
| Upload subaward documents to sponsor portal | 2025-12-19
| Upload documents to Kuali | 2025-12-19
| Upload documents to sponsor portal (Cayuse, Research.gov, etc.) | 2025-12-19
Final Project Title, Start/End Dates, Budget, Questionnaire in Kuali |  | 2025-12-19 |  |  | PI emails Charles Greer approval to submit to SPA late
Miminim documents route Kuali |  | Miminim documents needed for each non-UCR subawards to route Kuali
Proposal Soliciation from Sponsor |  | Letter of Institutional Commitment (non-UC) or Multi-Campus Agreement (UC)
Scope of Work/Abstract |  | Scope of Work
Budget |  | Budget
Budget Justification |  | Budget Justification
Key Personnel Effort
Questionnaire Answers (submitted with request for budget proposal form)
System | Resources
Kuali | Request a budget proposal
Kuali | Using data validation and removing errors
Kuali | PI Certification
Kuali | Effort Calculation
Kuali | Uploading Documents
Kuali | Download Current & Pending
Cayuse | Uploading Documents in Cayuse
Cayuse | Using data validation and removing errors
2025-2026 UCR Holidays/Administrative Offices Closed
2025-07-04
2025-11-11
2025-11-27
2025-11-28
2025-12-24
2025-12-25
2025-12-26
2025-12-27
2025-12-28
2025-12-29
2025-12-30
2025-12-31
2026-01-01
2026-01-19
2026-02-16
2026-03-27
2026-05-25
2026-06-19
Formulas:
If Late = IF(AND(ISNUMBER(A1), ISNUMBER([Due]), ([Due] - TODAY()) < 19), "PI launches their own Kuali", "")
If Late = IF(AND(ISNUMBER(A1), ISNUMBER([Due]), ([Due] - TODAY()) < 7), "Notification less than 7 days can result in the inability to provide a budget that aligns with institutional & sponsor policy", "")